## Slide 1: Plumbing Web Site Project
Presented By: Ava Thompson
10/30/2025

## Slide 2: Scope of Work
Fast, secure, conversion-first site
WordPress build with local SEO
Clear CTAs, booking flow
Technical SEO, schema, analytics
Accessibility, security, ownership
Reviews engine, social setup
90-day content cadence
4–6 week path to value

## Slide 3: Estimate
Website creation cost: $5,400
Local SEO cost: $2,000
Social profiles setup: $1,400
Subtotal $8,800; tax $880
Grand total due: $9,680
Yearly site review: $499
Monthly services total: $1,085
Estimate subject to change
Products and Services | Price | Quantity | Amount
Website creation | $5,400.00 | 1 | $5,400.00
Local SEO | $2,000.00 | 1 | $2,000.00
Social Media Profiles | $1,400.00 | 1 | $1,400.00
Total Products and Services Costs |  |  | $8,800.00

## Slide 4: Estimate
Website creation cost: $5,400
Local SEO cost: $2,000
Social profiles setup: $1,400
Subtotal $8,800; tax $880
Grand total due: $9,680
Yearly site review: $499
Monthly services total: $1,085
Estimate subject to change
Ongoing Yearly Costs |  |  | 
Site Review & Modifications | $499.00 | 1 | $499.00
Total Ongoing Yearly Costs |  |  | $499.00

## Slide 5: Estimate
Website creation cost: $5,400
Local SEO cost: $2,000
Social profiles setup: $1,400
Subtotal $8,800; tax $880
Grand total due: $9,680
Yearly site review: $499
Monthly services total: $1,085
Estimate subject to change
Ongoing Monthly Costs |  |  | 
Site Care & Local Growth | $995.00 | 1 | $995.00
Call Tracking | $45.00 | 1 | $45.00
Paid Ads Management | $45.00 | 1 | $45.00
Total Ongoing Monthly Costs |  |  | $1,085.00

## Slide 6: Estimate
Website creation cost: $5,400
Local SEO cost: $2,000
Social profiles setup: $1,400
Subtotal $8,800; tax $880
Grand total due: $9,680
Yearly site review: $499
Monthly services total: $1,085
Estimate subject to change
Summary | 
Subtotal (excluding yearly/monthly) | $8,800.00
Shipping | $0.00
Sales Tax | $880.00
Grand Total | $9,680.00

## Slide 7: Key Performance Indicators
Predictable pipeline via KPIs
Calls, bookings, Eastside coverage
4-6 week launch; 3-4 month ramp
30-50 qualified calls monthly
Top-10 for 8-10 keywords
8-12% conversion; 10+ reviews
200+ clicks by month three
Mobile LCP under 2.5s

## Slide 8: Maintenance Plan
Managed hosting, updates, backups
Local SEO and site care
Security hardening and patching
Analytics, attribution, KPI reporting
GBP upkeep and citations
Content tweaks, light CRO tests
Optional paid ads management
Non-contract terms, SLAs, safeguards

## Slide 9: Implementation Schedule
Kickoff and content intake
Sitemap and brief finalized
Wireframes and design comps
Copywriting up to 10 pages
WordPress build and SEO setup
QA, revisions, and launch
Local SEO and citations
Social setup and content plan
Implementation Task Description | Start Date | End Date | Duration
Project kickoff & content intake (logos, services, photos) | 10/30/2025 | 10/31/2025 | 2
Sitemap & brief (value props, CTAs) | 11/1/2025 | 11/1/2025 | 1
Wireframes for core pages | 11/2/2025 | 11/4/2025 | 3
Visual design comps | 11/5/2025 | 11/7/2025 | 3
Copywriting for up to 10 pages | 11/8/2025 | 11/11/2025 | 4
WordPress setup & build | 11/12/2025 | 11/16/2025 | 5
Forms, click-to-call, GA4/Search Console, basic on-page SEO | 11/17/2025 | 11/17/2025 | 1
QA & client review | 11/18/2025 | 11/19/2025 | 2
Revisions & launch prep | 11/21/2025 | 11/22/2025 | 2
Go-live & smoke test | 11/23/2025 | 11/23/2025 | 1
Google Business Profile claim/optimize | 11/24/2025 | 11/25/2025 | 2
Citations/NAP cleanup | 11/26/2025 | 11/29/2025 | 4
Local service-area pages | 11/30/2025 | 12/3/2025 | 4
Review engine setup | 12/4/2025 | 12/4/2025 | 1
Social profiles setup | 12/5/2025 | 12/6/2025 | 2
Social branding kit | 12/7/2025 | 12/8/2025 | 2
90-day content plan | 12/9/2025 | 12/10/2025 | 2

## Slide 10: Implementation Schedule
Kickoff and content intake
Sitemap and brief finalized
Wireframes and design comps
Copywriting up to 10 pages
WordPress build and SEO setup
QA, revisions, and launch
Local SEO and citations
Social setup and content plan
Start Date | 10/30/2025
Completion Date | 12/10/2025
Days to Complete | 42

## Slide 11: Client Responsibilities
Provide licenses, insurance, pricing
Deliver reviews, photos, bios
Submit brand assets, organized
Confirm domain, hosting, Google access
Approve sitemap, wireframe, staging
Consolidate feedback, designate approvers
Attend check-ins, respond promptly
Maintain NAP accuracy, notify changes

## Slide 12: Packages
Tiered packages, growth-aligned investment
Essentials: 8–10 pages, baseline SEO
Growth: city pages, starter content
Dominance: scale SEO, PPC, content
Site Care: ongoing SEO, maintenance
A La Carte: targeted add‑ons
Transparent ownership, analytics, compliance
Defined timeline, phased delivery options

## Slide 13
Sparksite Studio
425 Willow Street
Suite 210
Redmond, WA 98052
www.sparksite.studio